## Slide 1: Director Memorandum 2025-74 Consideration to Award Professional Services Contract and Approve Master Consulting Agreement for Architectural and Engineering Services – Bldg. Project
August 7, 2025

## Slide 2: Background
Past efforts:
  Construction of a new two-story glass “wavy” building on the vacant lot diagonally across from the current Administration Building at 3590 Rubidoux Blvd. (2008-2017)
  Acquisition of the County Fleet Services Building at 5293 Mission Blvd., either independently or in partnership with the City of Jurupa Valley (2018-2021)
  Utilization of the Rubidoux Family Resource Center (5473 Mission Blvd.) for administrative functions, with a remodel of the existing facility at 3590 Rubidoux Blvd. for field operations (2021-2024)

## Slide 3: Background
Current effort:
  Remodel of existing Administrative Building and construction of a new Operations Building on the District-owned 2.3-acre parcel diagonally across the street
  Single campus
    Consolidate field and administrative functions
    More collaborative and efficient work environment

## Slide 4: Single Campus
.67-acres
2.3-acres

## Slide 5: Project Overview
Administration Building (3590 Rubidoux)
  Modernize (preferred)
  Reconfiguration of interior space for operational efficiency and customer service
  ADA upgrades
  Seismic retrofitting
  Energy efficient measures
  Updated audio/visual systems and furniture systems
  Exterior improvements:
    Relocate emergency generator and fuel tank
    Enhance pedestrian and vehicle circulation

## Slide 6: Project Overview
New Operations Center (2.3-acre vacant lot)
  Pre-engineered or custom metal building with administrative areas
  Vehicle maintenance bays
  Secure storage
  Employee facilities
  Exterior improvements:
    Dedicated parking
    Fuel and generator locations
    EV charging infrastructure
    Stormwater management
    Fencing
    Lighting
    Vehicle washing station
    Site security

## Slide 7: Project Overview
Scope
  Design (concurrently) and construction (concurrently or close succession)
  Admin Building:
    Preference: retain and modernize building
    But…
    Evaluation of existing building: hazmat survey, as-built drawings, and structural/condition analysis with scenario options (remodel vs. replacement cost)

## Slide 8: Scope of Services and Deliverables
Scope
  Facility Assessment
  Programming & Space Planning
  Design Services
  Permitting & Agency Coordination
  Cost Estimating
  Bid & Construction Support
  Stakeholder Engagement
  Furniture & A/V Design Support
  Need: Architectural and Engineering Design Services Firm RFP

## Slide 9: Request For Proposal (RFP)
Released: May 15, 2025
Mandatory site walk: May 27, 2025
Due date: July 3, 2025
Selection Criteria:
  Project Understanding / Approach – 45 Points
  Firm Qualifications and Experience – 40 Points
  Project Schedule – 15 Points
4 proposals received
2 interviews conducted
1 clear firm……..

## Slide 10: Preferred Firm
SVA Architects
  Demonstrated strongest understanding of the District’s vision, scope, implementation challenges and preferred schedule
  Ability to enter into Master Consulting Agreement (reviewed by General Counsel)
  Relevant work:
    City of Jurupa Valley City Hall Remodeling & Building Addition
    Monte Vista Water District Master Plan & Renovation

## Slide 11: Project Schedule
Now – June 2026 (1 year): Pre-Design through Bid Support
July 2026 – July 2027 (1 year): Construction, close-out, and move-in
Schedule subject to change

## Slide 12: Budget Considerations
Proposed Cost: $1,324,795 (all scope items)
Proposed Contingency: $175,205 (~13%)
Proposed Total Authorization: $1,500,000

## Slide 13: Budget Considerations
Proposed Budget Amendments:
  General Fund Ln. 57 ‘Admin. Bldg. Proj’ - $675,000 to $1,500,000
    Funding Source: General Fund LAIF Unrestricted Property Tax Reserve
    Current Balance: ~$6.5 million
  General Fund Ln. 60 ‘Transfer from Proj Admin Bldg Reserves’ - $675,000 to $0
    Note: Amount reduced as these are restricted loan proceeds to be utilized towards construction costs

## Slide 14: Recommendation
Staff recommends the Board of Directors consider the following actions:
  Accept Fee Proposal and enter into Master Consulting Agreement with SVA Architects for Bldg. Project.
  Authorize architectural and engineering design costs up to $1,500,000.
  Issue a TO to SVA Architects for $1,324,795 and allow issuance of individual TO’s for unforeseen design costs up to $1,500,000.
  Amend the FY 2025|2026 General Fund Budget
    Ln. 57: $675,000 to $1,500,000; Ln. 60: $675,000 to $0
  Utilize $1,500,000 from GF Unrestricted Property Tax Reserve

## Slide 15
Rubidoux Community Services District
Office: 951.684.7580
www.rcsd.org
Questions
15