## Slide 1
RUBIDOUX COMMUNITY SERVICES DISTRICT
Fire Station 38 Roof Replacement Update
October 15, 2026
BOARD PROGRESS REPORT | OCTOBER 2026

## Slide 2
Background & Board Authorization
Summarize the emergency, prior repairs, and Board action authorizing the work.
RUBIDOUX COMMUNITY SERVICES DISTRICT | FIRE STATION 38 ROOF UPDATE
01
BOARD ACTION
DM 2026-85 (October 1, 2026) – Board approved emergency award of the Fire Station 38 Tile Roof Replacement Project to HYT Construction, Inc.
• Scope:
- Demo existing tile, flashings, underlayment, and roof sheathing
- Install new plywood, full-deck water proofing, new flashings and drainage components, concrete tile roofing • Project Period: October 5 – October 30 • Amount: $270,000; plus $25,000 District-controlled allowance
• Other Considerations:
- All work coordinated with District and station personnel
- Preserve emergency access, protect apparatus and occupants
- Keep open roof area watertight at the end of every workday
- Daily updates/photos
[Optional caption or key detail]
CURRENT STATUS: PHASED DEMO AND INSTALL OF PLYWOOD AND WATER PROOFING

## Slide 3
Daily Progress Update — Day 01
10/5/26 | CONTRACT EXECUTED – DEMOLITION STARTED
RUBIDOUX COMMUNITY SERVICES DISTRICT | FIRE STATION 38 ROOF UPDATE
02

## Slide 4
Daily Progress Update — Day 02
10/6/26 | DEMOLITION TILE REMOVAL - CONTINUED
RUBIDOUX COMMUNITY SERVICES DISTRICT | FIRE STATION 38 ROOF UPDATE
03

## Slide 5
Daily Progress Update — Day 03
10/7/26 | DEMOLITION TILE REMOVAL - CONTINUED
RUBIDOUX COMMUNITY SERVICES DISTRICT | FIRE STATION 38 ROOF UPDATE
04

## Slide 6
Daily Progress Update — Day 04
10/8/26 | DEMOLITION TILE AND PLYWOOD REMOVAL; PLYWOOD INSTALL
RUBIDOUX COMMUNITY SERVICES DISTRICT | FIRE STATION 38 ROOF UPDATE
05

## Slide 7
Daily Progress Update — Day 05
10/9/26 | DEMOLITION OF EXISTING AND INSTALL OF NEW PLYWOOD; INSTALL WEATHER PROOFING MATERIAL
RUBIDOUX COMMUNITY SERVICES DISTRICT | FIRE STATION 38 ROOF UPDATE
06

## Slide 8
Daily Progress Update — Day 06
10/10/26 | DEMOLITION OF EXISTING AND INSTALL OF NEW PLYWOOD; INSTALL WEATHER PROOFING MATERIAL; WEATHER TIGHT SEAL
RUBIDOUX COMMUNITY SERVICES DISTRICT | FIRE STATION 38 ROOF UPDATE
07

## Slide 9
Daily Progress Update — Day 07 and Day 08
10/11 – 10/12/26 | NO WORK DUE TO RAIN
RUBIDOUX COMMUNITY SERVICES DISTRICT | FIRE STATION 38 ROOF UPDATE
08
Station 38 Captain noted the weather proofing seemed to hold during the rain with no major issues.

## Slide 10
Daily Progress Update — Day 09
10/13/26 | DEMOLITION OF EXISTING AND INSTALL OF NEW PLYWOOD; INSTALL WEATHER PROOFING MATERIAL
RUBIDOUX COMMUNITY SERVICES DISTRICT | FIRE STATION 38 ROOF UPDATE
09

## Slide 11
Daily Progress Update — Day 10
10/14/26 | DEMOLITION OF EXISTING AND INSTALL OF NEW PLYWOOD; INSTALL WEATHER PROOFING MATERIAL
RUBIDOUX COMMUNITY SERVICES DISTRICT | FIRE STATION 38 ROOF UPDATE
10

## Slide 12
Upcoming Action Items & Next Steps
Close out the emergency work, document completion, and report back to the Board.
RUBIDOUX COMMUNITY SERVICES DISTRICT | FIRE STATION 38 ROOF UPDATE
12
UP NEXT
• By end of week: Finish demo of existing plywood and install of new plywood and underlayment • By end of week: Battens laid out and installed • Monday (10/19): Tile scheduled for delivery
ADDITIONAL BUDGET REQUESTS
• None at this time, District controlled contingency of $25,000 remains available for slight change orders
BOARD FOLLOW-UP
• Target Completion remains October 30, 2026
• Next update: November 5, 2026
QUESTIONS?
RECOMMENDATION
• Receive and file status update